## Shayan
UAT Results - Shayan (technically advanced)
ID | Role | Scenario | Steps | Expected Result | Actual Result | Pass/Fail | Notes
UAT-01 | Admin | Deploy election | 1. Open Admin page. 2. Enter title, candidates, time window, relayer, and optional Semaphore address. 3. Deploy election. | Election deploys successfully and returns a contract address. | Completed deploy flow quickly and entered correct values without assistance. | Pass | Technically advanced; no confusion with admin fields.
UAT-02 | Admin | Register voters | 1. Open the deployed election. 2. Paste or import voter wallet addresses. 3. Submit registerVoters. | Wallet addresses are added to the election allowlist successfully. | Imported and registered voter addresses on the first attempt. | Pass
UAT-03 | Voter | Link identity during PENDING | 1. Open election page. 2. Go to Link Identity. 3. Sign the identity payload and submit. | Identity links successfully while election status is PENDING. | Understood identity linking and signature prompts immediately. | Pass
UAT-04 | Voter | Prevent late identity linking | 1. Wait until election status is OPEN. 2. Try to link identity again. | Link request is rejected with a clear error message. | Confirmed that late linking was blocked and understood the reason. | Pass
UAT-05 | Voter | Cast vote | 1. Open ballot page. 2. Select a candidate. 3. Generate proof and submit vote through relayer. | Vote succeeds and a receipt is displayed to the voter. | Completed vote quickly and copied the receipt correctly. | Pass
UAT-06 | Voter | Verify receipt | 1. Copy the returned receipt. 2. Open the receipt page. 3. Check receipt inclusion. | Receipt inclusion check succeeds. | Verified the receipt successfully on the first try. | Pass
UAT-07 | Observer | View tally and public election data | 1. Open tally or election status page. 2. Review candidates, status, and tally. | Public election data loads correctly during and after voting. | Read tally and status correctly without help. | Pass
UAT-08 | Admin | Close election early | 1. Open Manage Existing Election. 2. Trigger closeEarly. 3. Refresh election status. | Election status changes to CLOSED. | Closed the election early successfully and refreshed state correctly. | Pass
UAT-09 | Voter | Kiosk mode ballot flow | 1. Launch kiosk mode with a direct election address. 2. Open the ballot page. 3. Attempt the normal voting flow. | Kiosk opens directly to the election ballot page and remains usable. | Kiosk flow felt straightforward and uncluttered. | Pass
UAT-10 | Voter | Mobile usability | 1. Open the app on a phone-sized screen. 2. Complete link, vote, and receipt flow. | Layout remains readable, controls stay usable, and the flow completes successfully. | Mobile layout remained usable and readable throughout. | Pass

## Farzaneh
UAT Results - Farzaneh (teacher)
ID | Role | Scenario | Steps | Expected Result | Actual Result | Pass/Fail | Notes
UAT-01 | Admin | Deploy election | 1. Open Admin page. 2. Enter title, candidates, time window, relayer, and optional Semaphore address. 3. Deploy election. | Election deploys successfully and returns a contract address. | Completed deploy flow with brief orientation to the page. | Pass | Slower learning curve than technical testers.
UAT-02 | Admin | Register voters | 1. Open the deployed election. 2. Paste or import voter wallet addresses. 3. Submit registerVoters. | Wallet addresses are added to the election allowlist successfully. | Completed voter registration successfully, but more slowly than Shayan. | Pass
UAT-03 | Voter | Link identity during PENDING | 1. Open election page. 2. Go to Link Identity. 3. Sign the identity payload and submit. | Identity links successfully while election status is PENDING. | Linked identity successfully after reading the prompts carefully. | Pass | Complained that the linking process felt unclear and could use simpler explanation.
UAT-04 | Voter | Prevent late identity linking | 1. Wait until election status is OPEN. 2. Try to link identity again. | Link request is rejected with a clear error message. | Understood that late linking is blocked after it was demonstrated. | Pass
UAT-05 | Voter | Cast vote | 1. Open ballot page. 2. Select a candidate. 3. Generate proof and submit vote through relayer. | Vote succeeds and a receipt is displayed to the voter. | Cast vote successfully after taking more time to confirm each step. | Pass
UAT-06 | Voter | Verify receipt | 1. Copy the returned receipt. 2. Open the receipt page. 3. Check receipt inclusion. | Receipt inclusion check succeeds. | Verified receipt successfully once shown where to paste it. | Pass
UAT-07 | Observer | View tally and public election data | 1. Open tally or election status page. 2. Review candidates, status, and tally. | Public election data loads correctly during and after voting. | Viewed tally and status correctly. | Pass
UAT-08 | Admin | Close election early | 1. Open Manage Existing Election. 2. Trigger closeEarly. 3. Refresh election status. | Election status changes to CLOSED. | Closed election early successfully with light guidance. | Pass
UAT-09 | Voter | Kiosk mode ballot flow | 1. Launch kiosk mode with a direct election address. 2. Open the ballot page. 3. Attempt the normal voting flow. | Kiosk opens directly to the election ballot page and remains usable. | Kiosk flow was usable but would benefit from simpler wording. | Pass
UAT-10 | Voter | Mobile usability | 1. Open the app on a phone-sized screen. 2. Complete link, vote, and receipt flow. | Layout remains readable, controls stay usable, and the flow completes successfully. | Completed the mobile flow successfully, but at a slower pace. | Pass

## Ali Reza
UAT Results - Ali Reza (dentist)
ID | Role | Scenario | Steps | Expected Result | Actual Result | Pass/Fail | Notes
UAT-01 | Admin | Deploy election | 1. Open Admin page. 2. Enter title, candidates, time window, relayer, and optional Semaphore address. 3. Deploy election. | Election deploys successfully and returns a contract address. | Completed deploy flow, but paused to understand several labels. | Pass | Some terminology was not immediately clear.
UAT-02 | Admin | Register voters | 1. Open the deployed election. 2. Paste or import voter wallet addresses. 3. Submit registerVoters. | Wallet addresses are added to the election allowlist successfully. | Completed registration successfully. | Pass
UAT-03 | Voter | Link identity during PENDING | 1. Open election page. 2. Go to Link Identity. 3. Sign the identity payload and submit. | Identity links successfully while election status is PENDING. | Linked identity successfully, but wallet setup and terminology were not desirable. | Pass | Wallet creation and setup was the least user-friendly part.
UAT-04 | Voter | Prevent late identity linking | 1. Wait until election status is OPEN. 2. Try to link identity again. | Link request is rejected with a clear error message. | Understood the late-link restriction after explanation. | Pass
UAT-05 | Voter | Cast vote | 1. Open ballot page. 2. Select a candidate. 3. Generate proof and submit vote through relayer. | Vote succeeds and a receipt is displayed to the voter. | Cast vote successfully once labels were clarified. | Pass | Some text was hard to read quickly.
UAT-06 | Voter | Verify receipt | 1. Copy the returned receipt. 2. Open the receipt page. 3. Check receipt inclusion. | Receipt inclusion check succeeds. | Verified receipt successfully after being reminded of the terminology used on the page. | Pass
UAT-07 | Observer | View tally and public election data | 1. Open tally or election status page. 2. Review candidates, status, and tally. | Public election data loads correctly during and after voting. | Viewed tally and status correctly. | Pass
UAT-08 | Admin | Close election early | 1. Open Manage Existing Election. 2. Trigger closeEarly. 3. Refresh election status. | Election status changes to CLOSED. | Closed election early successfully. | Pass
UAT-09 | Voter | Kiosk mode ballot flow | 1. Launch kiosk mode with a direct election address. 2. Open the ballot page. 3. Attempt the normal voting flow. | Kiosk opens directly to the election ballot page and remains usable. | Kiosk flow was understandable, but larger text would help. | Pass
UAT-10 | Voter | Mobile usability | 1. Open the app on a phone-sized screen. 2. Complete link, vote, and receipt flow. | Layout remains readable, controls stay usable, and the flow completes successfully. | Completed mobile flow, but struggled to read some text and terminology. | Pass | Readability should be improved.

## Michael
UAT Results - Michael (biochemical engineering student)
ID | Role | Scenario | Steps | Expected Result | Actual Result | Pass/Fail | Notes
UAT-01 | Admin | Deploy election | 1. Open Admin page. 2. Enter title, candidates, time window, relayer, and optional Semaphore address. 3. Deploy election. | Election deploys successfully and returns a contract address. | Completed deploy flow very quickly, but initially skipped over one field and had to go back. | Pass | Moved faster than the interface messaging expected.
UAT-02 | Admin | Register voters | 1. Open the deployed election. 2. Paste or import voter wallet addresses. 3. Submit registerVoters. | Wallet addresses are added to the election allowlist successfully. | Completed registration quickly. | Pass
UAT-03 | Voter | Link identity during PENDING | 1. Open election page. 2. Go to Link Identity. 3. Sign the identity payload and submit. | Identity links successfully while election status is PENDING. | Linked identity successfully, but moved too fast and missed one text box before correcting. | Pass
UAT-04 | Voter | Prevent late identity linking | 1. Wait until election status is OPEN. 2. Try to link identity again. | Link request is rejected with a clear error message. | Triggered or observed late-link rejection correctly. | Pass
UAT-05 | Voter | Cast vote | 1. Open ballot page. 2. Select a candidate. 3. Generate proof and submit vote through relayer. | Vote succeeds and a receipt is displayed to the voter. | Vote submitted successfully, but he moved too quickly past the receipt display and lost the receipt. | Pass | Receipt was generated, but not saved by the tester.
UAT-06 | Voter | Verify receipt | 1. Copy the returned receipt. 2. Open the receipt page. 3. Check receipt inclusion. | Receipt inclusion check succeeds. | Could not verify receipt because the receipt was not saved after voting. | Fail | Only failed UAT step for this tester.
UAT-07 | Observer | View tally and public election data | 1. Open tally or election status page. 2. Review candidates, status, and tally. | Public election data loads correctly during and after voting. | Viewed tally and status correctly. | Pass
UAT-08 | Admin | Close election early | 1. Open Manage Existing Election. 2. Trigger closeEarly. 3. Refresh election status. | Election status changes to CLOSED. | Completed close-early action successfully. | Pass
UAT-09 | Voter | Kiosk mode ballot flow | 1. Launch kiosk mode with a direct election address. 2. Open the ballot page. 3. Attempt the normal voting flow. | Kiosk opens directly to the election ballot page and remains usable. | Kiosk flow was fast, but some text boxes were easy to skip if rushing. | Pass
UAT-10 | Voter | Mobile usability | 1. Open the app on a phone-sized screen. 2. Complete link, vote, and receipt flow. | Layout remains readable, controls stay usable, and the flow completes successfully. | Mobile flow completed quickly, but the interface could do more to highlight important fields. | Pass

## Sarah
UAT Results - Sarah (artist)
ID | Role | Scenario | Steps | Expected Result | Actual Result | Pass/Fail | Notes
UAT-01 | Admin | Deploy election | 1. Open Admin page. 2. Enter title, candidates, time window, relayer, and optional Semaphore address. 3. Deploy election. | Election deploys successfully and returns a contract address. | Initially mixed up the Semaphore and relayer addresses, then corrected the fields and deployed successfully. | Pass | Careful reader; recovered by following the UI text closely.
UAT-02 | Admin | Register voters | 1. Open the deployed election. 2. Paste or import voter wallet addresses. 3. Submit registerVoters. | Wallet addresses are added to the election allowlist successfully. | Completed registration successfully by following the instructions carefully. | Pass
UAT-03 | Voter | Link identity during PENDING | 1. Open election page. 2. Go to Link Identity. 3. Sign the identity payload and submit. | Identity links successfully while election status is PENDING. | Linked identity successfully after re-reading the page text closely. | Pass
UAT-04 | Voter | Prevent late identity linking | 1. Wait until election status is OPEN. 2. Try to link identity again. | Link request is rejected with a clear error message. | Understood the late-link restriction and accepted the message. | Pass
UAT-05 | Voter | Cast vote | 1. Open ballot page. 2. Select a candidate. 3. Generate proof and submit vote through relayer. | Vote succeeds and a receipt is displayed to the voter. | Cast vote successfully and followed the instructions carefully. | Pass
UAT-06 | Voter | Verify receipt | 1. Copy the returned receipt. 2. Open the receipt page. 3. Check receipt inclusion. | Receipt inclusion check succeeds. | Verified receipt successfully. | Pass
UAT-07 | Observer | View tally and public election data | 1. Open tally or election status page. 2. Review candidates, status, and tally. | Public election data loads correctly during and after voting. | Viewed tally and status correctly. | Pass
UAT-08 | Admin | Close election early | 1. Open Manage Existing Election. 2. Trigger closeEarly. 3. Refresh election status. | Election status changes to CLOSED. | Closed election early successfully. | Pass
UAT-09 | Voter | Kiosk mode ballot flow | 1. Launch kiosk mode with a direct election address. 2. Open the ballot page. 3. Attempt the normal voting flow. | Kiosk opens directly to the election ballot page and remains usable. | Kiosk flow felt straightforward once the correct addresses were entered. | Pass
UAT-10 | Voter | Mobile usability | 1. Open the app on a phone-sized screen. 2. Complete link, vote, and receipt flow. | Layout remains readable, controls stay usable, and the flow completes successfully. | Completed mobile flow successfully; cautious reading reduced mistakes. | Pass

## Issue Log
Issue Log - UAT Findings (5 users)
Issue ID | Related UAT ID | Summary | Severity | Status | Notes
ISSUE-01 | UAT-03 | Identity linking flow is not immediately understandable for non-technical users. | Medium | Open | Raised most clearly by Farzaneh; the link process needs simpler explanation and clearer step guidance.
ISSUE-02 | UAT-03 | Wallet setup is too technical and undesirable for some users. | High | Open | Ali Reza specifically disliked the wallet setup step; this is a major usability barrier for broader adoption.
ISSUE-03 | UAT-05 | Some UI text and terminology are hard to read or understand quickly. | Medium | Open | Observed by Ali Reza and partly by Farzaneh. Larger text and simpler wording would help.
ISSUE-04 | UAT-06 | Receipt handling is too easy to miss; users can lose the receipt after voting. | High | Open | Michael lost the receipt immediately after voting and then failed receipt verification.
ISSUE-05 | UAT-01 | Address fields are easy to confuse, especially Semaphore vs relayer address. | Medium | Open | Sarah mixed up the two addresses before correcting herself. Stronger labels or validation would help.
ISSUE-06 | UAT-09 | Fast users can skip over important text boxes or messages. | Medium | Open | Michael moved too quickly and missed fields/instructions. More visual emphasis is needed for critical inputs.